## Slide 1: Core Operating System
A Go Forward Strategy

## Slide 2: Presentation Structure
Overall Approach
Individuals and groups interviewed
OMSV Background and Vision for COS
Finding and analysis
  Value Assessment
  COS Procurement Assessment
  COS Solution Delivery Assessment
Go-Forward Option Analysis
Go-Forward Recommendations / Next steps

## Slide 3: Our Approach
Options
Go Forward Recommendations
COS
Value
Assessment
Procurement
Assessment
Solution
Delivery
General Findings
General Findings

## Slide 4: Organizations and Individuals Met / Interviewed
OSMV
  Deidre Moran, Stephanie Melvin. Steve Martin
ISB
  Bobbie Sadler; Stuart Cayzer; Harold Trenchar; Robert Bartnik; Tanaka, Mitsuko; Barnsley, Carol; Mahoney, Glenn; Chatupromwong, Bert S; Burnell, Don; Shapka, Nataliya; Tocher, Rob; Lee, Jason K; Ford, Leo D; Martin, Yvonne; Dixon, Merla E
Helios
  Andrew Lamoureux, Kyle Stamm
CGI
  Scott Daws, Gordon Stickney
OCIO
  Derek Rutherford, Albert Wilhelm
ICBC
  Mark Lucas

## Slide 5: Background
“Service Delivery Challenges: OSMV’s current business delivery model is facing a number of challenges having a direct impact on clients/partners, business users, and management. A significant portion of these challenges are driven by the lack of functionality in the existing systems which support they delivery of OSMV’s core programs.”
Customers
Low quality data transmission
Late information submission
Channels are not interactive
Errors in letter templates
IVR is cumbersome
Business
Siloed view of customers
Routine activities not automated
Focus on paper based processing
Multiple business work around to handle systems issues
Process & systems challenges result in reversals of decisions
System
Costly and lengthy process for minor systems changes
Frequent unplanned system outages during core hours
Regular errors integrating drivers and core systems
Scan system does not meet needs
Leadership
System rigidities stifle innovation
Limited reporting & program evaluation
Policy driven inefficiencies (e.g. paper retention)
Staff dissatisfaction/reduced engagement

## Slide 6: Background
“Business and Systems Vision: The OSMV has a multi-faceted vision of how the organization would like to leverage technology in order to deliver their services in an effective, streamlined, and holistic manner.”
Streamlined & Interactive Client Service
Simplifying key client touch points with a focus on leveraging technology to facilitate faster service, and streamline backend processing where there are sufficient cost and service benefits to justify capital investments
One-Client Approach
Integrating operations of road safety programs and embedding a one client processing approach, systems infrastructure and mindset. The primary objective is to harmonize outcomes across program areas, and to capitalize on opportunities to leverage information across programs.
Reliable and Responsive Systems Infrastructure
Laying the foundation for OSMV renewal by developing a systems infrastructure with reliable uptime performance and that is in tune with current business rules and needs, and that facilitates more effective processing, reporting, documentation and communications.
Accelerated Improvement in Road Safety Outcomes
Creating a culture of innovation to focus on getting the most out of available resources and implementing / improving road safety programs. Organizational capacity to take on new & enhanced programs will be created through an ambitious redesign and streamlining of existing programs with a focus on increased efficiency.
Notes: The color of this and next slide should be similar to previous slide…

## Slide 7: Background
Road Safety Leadership
Making compelling cases for new road safety programs & polices that will drive significant improvement in road safety outcomes by developing & leveraging business intelligence, policy and strategic planning capabilities.
“Business and Systems Vision: The OSMV has a multi-faceted vision of how the organization would like to leverage technology in order to deliver their services in an effective, streamlined, and holistic manner.”

## Slide 8: Core Operating System
Value Assessment
COS
Value
Assessment
Procurement
Assessment
Solution
Delivery

## Slide 9: Value Creation Framework
Value Delivery
(Execution)
Value Definition
(Desired Outcomes)
Value Management
(Governance)
Accountability Framework
Quality Assurance Framework
Performance Management Framework
Value Creation
Copyright Vi³ Consulting Inc.

## Slide 10: COS Overall Value Assessment
Quality
Effectiveness
Effective Decision Making
Efficient Execution
Quality
High Quality Results
Effectiveness
Effective Decision Making
High Quality Results
Effective Decision Making
Efficient Execution
High Quality Results
Effectiveness
Effective Decision Making
High Quality Results
Efficiency
Quality
Effectiveness
Effective Decision Making
Efficient Execution
Quality
High Quality Results
Effectiveness
Effective Decision Making
High Quality Results
COS
Outcome Management COS had a clearly defined problem definition supported by a clearly defined set of outcomes for its benefit realization
ICBC?

## Slide 11: COS Overall Value Assessment
Quality
Effectiveness
Effective Decision Making
Efficient Execution
Quality
High Quality Results
Effectiveness
Effective Decision Making
High Quality Results
Effective Decision Making
Efficient Execution
High Quality Results
Effectiveness
Effective Decision Making
High Quality Results
Efficiency
Quality
Effectiveness
Effective Decision Making
Efficient Execution
Quality
High Quality Results
Effectiveness
Effective Decision Making
High Quality Results
COS
Program Delivery Execution lacked coordination and integration in both planning and control.
COS
Governance Management COS had a set of siloed accountability with great deal of inter-dependencies between the Vendor, ITSD, OSMV and ICBC.
Poor Results
Value Creation
COS
Outcome Management COS had a clearly defined problem definition supported by a clearly defined set of outcomes for its benefit realization
ICBC?
Silo Accountability
Inadequate Performance Monitoring

## Slide 12: Core Operating System
Procurement Assessment
COS
Value
Assessment
Procurement
Assessment
Solution
Delivery

## Slide 13: Procurement Assessment
New Technology
Multiple Partners
Change in Business Processes across multiple organizations
Unknown data migration and data cleansing
Project Inter-dependencies
Silo accountability – Multiple PMs
Fixed Price Procurement
Inadequate bid response reviews
H
H
H
H
H
H
H
H

## Slide 14: Procurement Assessment (e.g., Environments)
Inadequate bid response reviews:
Section 5.2.1 (Project Initiation) “a key activity of the Project Initiation Phase is to determine the Environment Plan which includes the following:
  Discussing and confirming the environments set up and timing of set up.
  Confirm software and hardware requirements of each of the environments.
Assumption 2 of Schedule A: “the development environment will be set up at CGI. The Test, Training and Production environments will be set up in the [Ministry] domain by [the ITSD].”
Assumption 16 of Schedule A: “a server meeting Microsoft specifications will be needed to run CRM for the anticipated volume of users…this server could contain the CRM server and the SQL server. An existing SQL server could also be used as long as it is on the same domain as the CRM server. The Province will provide a single virtual server which will be adequate for this purposes. Performance of the overall application is a shared responsibility that includes both the design and architecture of the solution and the production hardware.”

## Slide 15: Procurement Assessment (e.g., Application / Environments)
Inadequate bid response reviews:
…server for the purposes of data exchange between DRIVERS and the CCMS…performance of the overall application is a shared responsibility that includes both the design and architecture of the solution and the production hardware.”
Refinement 8 of Schedule A says: “ Test, Training and Production environments will be set up in a timely manner by the Province in the [Ministry] domain maintained by the ITSD…”
Refinement 8 of Schedule A goes on to say: “the environment requirements and delivery scheduled will be defined and agreed upon during the Project Initiation Phase.”
Section 2.1 (Overview) says: “changes may also be required to ICBC DRIVERS interface and other partner interfaces that will feed into the new COS and DF web. Some changes may also be necessary to the ICBC and other partner organizations systems and will be made by the partner organization. However, they will need to be coordinated with the changes required to import the data to the new COS and DF web.”

## Slide 16: Procurement Assessment Summary
COS Procurement should have never been Fixed Price
Many items were left to be finalized in the Project Kick-off phase:
  Project planning with RPO, AG ITSD;
  Planning sessions to define ICBC engagement approach
Vendor should have been responsible for the overall technology solution
There should have been an independent review to assess risks associated with the winning bid in reference to the vendor’s proposed approach and methodology
There should have been a clear gated approach for both payment as well as approval for proceeding to the next phase
It was unclear from the requirements through to RFP, contract award and execution how COS fits into a sector wide capital investment.

## Slide 17: Core Operating System
Solution Delivery
COS
Value
Assessment
Procurement
Assessment
Solution
Delivery
Technology Assessment
    Application
    Data
    Infrastructure
    COTS
Business Assessment
    User
    Organizational
Project / Program Management

## Slide 18: Application Assessment
The COTS solution had too many gaps and required customization due to unique set of business requirements
None of the Iterations were complete prior to the design and development of the next Iteration
Changes in requirements resulted in changes in the Application design and development during the development phase
Application had a silo accountability and little planning for full integration
  ICBC responsible for their application modifications / Development
  CGI responsible for main on-line application
  ISB / OSMV authentication and security, image repository
Considerable challenges with application testing as a result of
  Incomplete iterations
  Too many bugs from previous iterations
  Lack of test environment (ISB and ICBC)

## Slide 19: Application Assessment
Confirmation of requirements in the following areas and their formal sign off by all stakeholders were not carried out or missing:
  OSMV Web
  Reporting
  OSMV and ICBC integration was flawed due to unclear responsibilities
  Supportability/Diagnostic tools/ Deployment tools
  Archive and long term data retention
  Security and Access
  Audit History and Reporting of audit history
Analysis and rework associated with ICBC Care Card work and infrastructure changes in ICBC from Webmethods to Weblogic
Look and Feel usability
  COTS solution with limited field validation capabilities
  COTS solution with user presentation limitation (e.g., inability to show Driver’s License # throughout the application)

## Slide 20: Application Completion Considerations
The following are outstanding items for completion of Release 1.0 of COS application, assuming requirements are complete and signed off:
  Confirming, Debugging, and functional testing of 400+ defects
  Debugging and Testing of Interfaces to other applications
  Design, development and Testing of Operational reports, System and Management Information Reports
  Completion of Functional Testing against “Ideal Business Processes” and Use Cases across the application (e.g., OSMV Web, Prohibitions and Impounds)
  Design, Development and execution of a comprehensive Integration Testing
  Design, Development and execution of a comprehensive System Performance Testing
  Design, Development and execution of a comprehensive User Acceptance Testing
  Design, Development and Testing of System Administration and Operations Manuals
  Requirements for the alignment of COS with RSS needs to be completed
COS Application has a considerable distance to go before “Go-Live”

## Slide 21: Data Assessment
Overall data migration was “capped at 1000 hours” by the vendor
The overall strategy document from early in the project is out of date
Future state Physical Data Model currently does not exists
Data Mapping is and will continue to be a challenge
  Not a direct map to the XRM system from existing application
Data Migration Scripts needs review and sign-off
No plan / effort has been dedicated to Data Cleansing
Data migration dress rehearsals plans are missing and clearly not aligned with application delivery
Data migration environment plan, setup and administration is yet to be finalized

## Slide 22: Data Completion Considerations
The following are outstanding items for completion of Release 1.0 of COS Data Readiness and its signed off:
Creation and completion of Data Migration charter including but not limited to covering:
  Data Mapping
  Dress Rehearsals with a clearly defined milestone plan including go-live data migration requirements
  Data requirements for Functional, Integration, System Performance and User Acceptance Tests
  Required Environments Specifications
  Development, testing of Data Migration Scripts
  Resource plan supported by estimated effort and approach required for Data Cleansing
  Data conversion and migration decision making process

## Slide 23: Infrastructure Assessment
Silo accountability for environment setup and management (ITSD, CGI, HP, ICBC, OMSV)
Building and changing environments as the project was unfolding
Instability in the test environments (hand off from CGI to ITSD)
ITSD did not meet any of its deadlines for having environments ready until 2012
A considerable amount of manual intervention for setting up the environments
There clearly was an environment plan supported by target dates, however, all the target dates were missed
Conducting activities in environment that were not designed for the activity (e.g., Functional Testing in Development Env. of ITSD)
Webmethods architecture and licensing was an infrastructure challenge (e.g., Web methods and Server availability)
Data Center availability was a challenge

## Slide 24: Infrastructure Assessment
Infrastructure delivery suffered from:
  Relationship between vendor and ITSD
  ITSD building environments at the same time CGI and OMSV trying to do functional testing
  CGI separate development environment that did not replicate ITSD environments
  Considerable learning curve
  MS Licensing
  Web Methods

## Slide 25: Infrastructure Completion Considerations
The following are outstanding items for completion of Release 1.0 of COS Infrastructure Readiness and its sign off:
Creation and completion of Infrastructure Readiness charter including but not limited to covering:
  Overall Technical Architecture and communication topology to be signed off by ITSD, Vendor, OSMV, and ICBC
  Infrastructure requirements for Functional, Integration, System Performance and User Acceptance Tests
  Required Environments for data migration
  Firewall and general architecture in Calgary/Kamloops must be incorporated into an overall deployment strategy

## Slide 26: MS Dynamics COTS Assessment
Customization
  To what extent is the application customized?
High
Most entities have been modified
New attributes have been added to each entity
Significant customization will still be needed to meet usability and data validation requirements

## Slide 27: MS Dynamics COTS Assessment
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data?
Key validation for data entry is missing
The data architecture is lacking in several ways including:
  Concessions on relationships. We have made several concessions on the relationships between entities as outlined in the logical data model. These concessions have been made to accommodate XRM limitations.
  Incomplete Conversion. We are not able to convert all data from existing applications ADP/VI and DF CMS into the new XRM repository.
  Physical Model includes split entities. For each entity, standard XRM attributes are included in one table, and customized attributes are included in a second table that has a 1-1 relationship with the first table.
  Physical Model is cluttered. There is no easy way to remove tables not in use. As a result, the COS solution will include many tables that are not even used.
High
Low

## Slide 28: MS Dynamics COTS Assessment
Low
ISB does not have experience with XRM
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data
Skillsets
  What is the level of readiness for ISB Support?
Low
High

## Slide 29: MS Dynamics COTS Assessment
Low
Every single deployment to government environments has been problematic even with vendor support and leadership
Configuration of the environment is an onerous and error-prone task
All errors in set-up are not easily detectable and require failed business transactions to identify.
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data
Skillsets
  What is the level of readiness for ISB Support?
Deployment
  What is the stability of the deployments?
Low
Low
High

## Slide 30: MS Dynamics COTS Assessment
Low
This assessment is based primarily on the integration with ICBC systems
Testing has repeatedly demonstrated errors in integration between ICBC and COS.
It is highly likely that there are many integration issues yet to be discovered with a production implementation as the testing environment and approach has not examined all production data conditions, or all production scenarios.
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data
Skillsets
  What is the level of readiness for ISB Support?
Deployment
  What is the stability of the deployments?
Integration
  What is the degree of confidence in the successful integration of the technology components?
Low
Low
Low
High

## Slide 31: MS Dynamics COTS Assessment
Medium
Deployments are problematic. Diagnosing problems with deployments has been challenging.
Application support models and tools have not been agreed to.
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data
Skillsets
  What is the level of readiness for ISB Support?
Deployment
  What is the stability of the deployments?
Integration
  What is the degree of confidence in the successful integration of the technology components?
Supportability
  How supportable is the application?
Low
Low
Low
Low
High

## Slide 32: MS Dynamics COTS Assessment
Low
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data
Skillsets
  What is the level of readiness for ISB Support?
Deployment
  What is the stability of the deployments?
Integration
  What is the degree of confidence in the successful integration of the technology components?
Supportability
  How supportable is the application?
Auditability
  Will the application meet all audit requirements?
Medium
Low
Low
Low
Low
High
The application maintains two sets of audit records, one in XRM and one in Webmethods
There is concern that fully using the auditing functionality in XRM will result in a significant performance hit
There is a further concern that tracking usage by ICBC and ServiceBC users will be problematic due to the fact that these users are not maintained in XRM.
Reporting of audit records has not been designed. Based on usability issues encountered so far, there is little confidence the reporting solution will be user-friendly.

## Slide 33: MS Dynamics COTS Assessment
Low
Customization
  To what extent is the application customized?
Data Management
  To what extent does COS effectively manage data
Skillsets
  What is the level of readiness for ISB Support?
Deployment
  What is the stability of the deployments?
Integration
  What is the degree of confidence in the successful integration of the technology components?
Supportability
  How supportable is the application?
Auditability
  Will the application meet all audit requirements?
Medium
Low
Low
Low
Low
High

## Slide 34: User & Organizational Assessment
COS Started with:
  Formal Orientation package received by all parties
  No Communication Package
  Training Needs Assessment was a silo approach
    OMSV did some internal training needs assessment
    ITSD did some internal training needs assessment
  No Plan for creation of a User Manual and System Admin. Manual
We found no formal documentation signed off by all parties identifying user groups (Technical, Administrative and functional Users) identifying their needs and expectations
  COS impact assessment must be an all encompassing enterprise assessment covering (ICBC, OMSV, ISB and 3rd party Service providers) and to a lesser degree police and other government agencies…

## Slide 35: Program Management Assessment
COS lost its Program / Project Director (Ms. Susan Ryan), this position was not filled with a replacement that allowed adequate time for COS
The OSMV PM had four hats:
  Fulfilled the role of the Project Director
  Overall Project Manager reporting to the Steering Committee
  COS Overall Business Lead
  Business Lead on RSS
Steering Committee:
  Did not follow a standard agenda
  Minutes were not taken
  Reporting lacked best practices
  Issues and Risks management lacked best practices
  Status reports were provided through Power Point Presentations not following best practices

## Slide 36: Program Management Assessment
Silo accountability
Project Management lacked structure and formality in managing and reporting on baseline plan, budget, quality and earned value
Working committees meeting discussed many concerns (e.g., TAC) that were not registered in the Risks and Issues logs and were not taken up to the SC for discussion and action
ICBC representation began a few months after project kick-off.

## Slide 37: Overall Assessment
Great deal of documented business and system requirements
A high risk procurement process
Inefficient and ineffective governance structure conceived from procurement through to execution
  RFP
  Vendor Response
  Contract Negotiation
  Orientation & Confirmation
  Customization and Integration
  Validation and Acceptance
A silo approach to what should have been a fully integrated business and system solution
Inefficient and ineffective Program and Project Management
  Project Planning
  Inter-dependency Management
  Issue and Risk Management
  Communication Management
  Project / Program Reporting, Monitoring and Oversight

## Slide 38: Core Operating System
Go Forward Recommendations
          Options Explored
          Overall Recommendation and Rational
          Governance
          Solution Delivery
          Procurement

## Slide 39: Options Explored
Reconvene the work with the current Vendor
Conduct an orderly shut sown of the project and reconvene at a later date
Stop current COTS Implementation and look for an alternative solution:
  Another COTS CRM
  Enhance Current System Functionality
  Custom Build COS application
  Explore integrating COS into RSS
Overall Recommendation: Explore integrating COS into RSS

## Slide 40: Recommendation Rational Organizations & Technology Alignment
RSS |  | COS
OSMV, ServiceBC, ICBC, ISB, SSBC Enforcement, Court Services, Ministry of Finance |  | OSMV, ServiceBC, ICBC, ISB, SSBC Guardian, Stroh
Shared Technology Components eJustice Integration Services Layer OSMV Image processing, letter generation, case management* ICBC Contraventions, Drivers, Vehicles Justice BI Customer Service Application(s) |  | Shared Technology Components eJustice Integration Services Layer OSMV Image processing, letter generation, case management* ICBC Contraventions, Drivers, Vehicles OSMV Reporting Customer Service Application(s)
Other Technology Components (not shared) Enforcement Systems & Road Side Technology Traffic Court Systems Online payments |  | Other Technology Components (not shared) 3rd party service provider systems
Example technology alignment – Both Programs:
Use eJustice Integration Services Layer to access and change the same Driver Information (Licences, & History)
Require collection of Justice operational and management reporting data, and tools to access and report on the data
Will provide data to front line service staff at ICBC and ServiceBC regarding road-safety programs

## Slide 41: Recommendation Rational Data Assets Alignment
RSS |  | COS
Shared Data Assets Driver History Road Safety Data Warehouse Driver Licence Vehicle Registration Prohibitions and Impounds |  | Shared Data Assets Driver History Road Safety Data Warehouse Driver Licence Vehicle Registration Prohibitions and Impounds
Other Data Assets (not shared) Contraventions: Tickets and Notices ICBC AR: Ticket and Notice Liabilities Enforcement Incidents and other roadside documents Traffic Court cases and liabilities |  | Other Data Assets (not shared) ICBC AR: Prohibition & Review Liabilities 3rd party service provider cases Cases from existing OSMV programs
Example technology alignment – Both Programs:
Use eJustice Integration Services Layer to access and change the same Driver Information (Licences, & History)
Require collection of Justice operational and management reporting data, and tools to access and report on the data
Will provide data to front line service staff at ICBC and ServiceBC regarding road-safety programs

## Slide 42: Recommendation Rational Business Functionality Alignment
RSS |  | COS
Shared Business Functions Justice Business Intelligence ServiceBC Point of Service ICBC Point of Service Prohibitions & Impoundments (create) |  | Shared Business Functions OSMV Business Intelligence ServiceBC Point of Service ICBC Point of Service Prohibition and Impoundments (record & manage)
Similar Business Functions OSMV Administrative Disputes: Notices OSMV Case Management: DIIP |  | Similar Business Functions OSMV Admin Disputes: Prohibitions & Impoundments OSMV Case Management:Driver Fitness, RDP, IIP
Other Business Functions (not shared) Enforcement Roadside documents Government Online Payment Traffic Court Disputes |  | Other Business Functions (not shared) 3rd party service provision (Stroh & Guardian)
Example process alignment – Both Programs:
Provide data to front line service staff at ICBC and ServiceBC regarding road-safety programs
Create business intelligence capabilities and provide reporting and analysis for Justice sector data
RSS creates prohibitions and impounds, COS stores and manages reviews of prohibitions and impounds

## Slide 43: Recommendation Rational RSS & COS Alignment
RSS and COS are highly related initiatives
RSS is much larger than COS, and COS is more specific to OSMV, however they:
  Share many of the same partners
  Share many technology components
  Require similar data
There are several key differences between RSS and COS:
  RSS has a heavy focus on production of all enforcement roadside documents
  RSS introduces new programs to the OSMV: Notice Disputes, and DIIP – COS is primarily focused on innovating existing OSMV programs
  RSS introduces Justice Sector Business Intelligence – COS introduces reporting only for OSMV

## Slide 44: Recommendations
Governance
Solution Delivery
Procurement
Options for Next Steps

## Slide 45: Governance
Considering its multi-jurisdictional nature, Governance should be based on a sector wide governance / approach rather than a silo approach
Governance structure MUST have the following critical roles and responsibilities:
  Program Sponsor that provides a sector wide prospective
  An overall vendor PM responsible for program planning and control and day to day operations adhering to best practices
  An overall Business lead responsible for collaborations and coordination of business SMEs and vendor liaison
  An overall Vendor Solution Architect responsible for the technology solution and supported by Application, data and Infrastructure architects
  Business and Technology working committees focused on:
    Program Orientation and Confirmation
    Customization and Integration
    Validation and Acceptance

## Slide 46: COS Solution Delivery Recommendations
Consolidate Business and System requirements:
  Ideal Business processes
  A prototype of the on-line application and user experience
  A detailed set of Use Cases in support of Ideal Business Processes and User Experience
  Detailed Specification for required real time and batch interfaces
  Detailed report Specification and layouts for:
    Operational;
    Technical and;
    Management Information reporting.
    Forms
  Any other business or System Requirements deemed necessary
Develop an Orientation and Confirmation package that would require sign off by ICBC, OSMV and ISB.
This document should be business oriented and address how the ``New Way of doing business`` will achieve desired Outcomes.

## Slide 47: Solution Delivery Recommendations
Complete RSS Ideal Business Processes and Major Functional Decomposition
Develop options on technology architecture design covering both RSS and COS functionality:
  Application
  Data
  Infrastructure
Ensure the proposed technology architecture is constrained by Government Technology and ISB “Know How”
This document must than be signed off by ICBC, OSMV and ISB.

## Slide 48: COS Reusable Assets High - Moderate
Business and conceptual system requirements
WebMethods
KOFAX image processing
Better understanding of User and Organizational Analysis
Use Cases
Knowledge and lessons learned
  Procurement, Governance, Integration, Partner Engagement
Logical Data Model
Current Application and user manuals as a foundation for a Prototype
Letter templates
Procured hardware and licenses
OSMV Web
.NET interface Stroh

## Slide 49: RSS and COS Program Options
Option 1
Integrate RSS and COS
Phase 1 |  | Phase2 | Phase 3
Oct – Dec 2012 | Jan – Mar 2013 | 2-4 Year Program | 1-2 Year Program
RSS Business Architecture & High Level Requirements
Phased Plan for
RSS and COS
RSS Development
COS Refined Detailed Requirements
COS Development
Option 2
Phase RSS and COS
Two proposed options to integrate and deliver RSS and COS program scope:
Phase 1 |  | Phase 3
Oct – Dec 2012 | Jan – Mar 2013 | 2-4 Year Program
RSS Business Architecture & High Level Requirements
COS Refined Detailed Requirements
Integrated Plan for RSS
Joint COS & RSS Development

## Slide 50: Procurement
All immediate next steps can be accomplished with current ISB and OSMV internal and external resources currently engaged in RSS and previously involved with COS.

## Slide 51: Q & A